## Read Me
To use the template
0 | File -> Make a copy, and share it among the members & the instructor (yan.chen01@sjsu.edu)
1 | In Members, enter member names & email for each role
(for 3-people group, delete 1 row of programmer)
2 | In Backlog, enter group number (members will be auto-filled in based on what you entered in 1)
Then document each task as a row:
| 2.1) | Choose milestone number
| 2.2) | Describe the task (method name, class name, etc.)
| 2.3) | Choose the member who's responsible for the task
| 2.4) | Choose the status
| 2.5) | For started (In Progress) tasks, enter the start date
| 2.6) | For Completed tasks, enter the end date
| 2.7) | Enter any additional notes
Color Codes (auto)
Red background: |  | Error
Red text: |  | Urgent task (due soon or blocking other tasks)
Grey text: |  | Completed
The last submission should have NO red background (no error) and all taskes should be in grey (all completed)
Possible Errors
| 1 & 2 | Missing group number or group members
| 2.5) | Missing start date for an In Progress or Completed task
OR Having start date for a Not Started task
| 2.6) | Missing end date for a Completed task
OR Having end date for an uncompleted task

## Members
Role | Name | Email
UI Designer | An hoang | banhkho5a@gmail.com
Programmer | Kanan Ibadzade | kananibadzade@gmail.com
Programmer | Efe Gur | efebahadirgur@gmail.com
Tester

## Backlog
Group - 11
Members: | An hoang , Kanan Ibadzade, Efe Gur
Milestone # | Task | Member | Status | Start Date | End Date | Comments
Milestone 2 | Implement occursOn | An hoang | Completed | 2024-10-11 | 2024-10-14
Milestone 2 | Test occursOn | Kanan Ibadzade | Completed | 2024-10-10 | 2024-10-14
Milestone 2 | Implement occursOn | Efe Gur | Completed | 2024-10-11 | 2024-10-14
Milestone 2 | UI Designer | An hoang | Completed | 2024-10-10 | 2024-10-14
Milestone 3 | Implement equals in Appointment for accurate comparison. | Kanan Ibadzade | Completed | 2024-11-01 | 2024-11-04
Milestone 3 | Add toString in subclasses for clear output. | An hoang | Completed | 2024-11-03 | 2024-11-04
Milestone 3 | Write JUnit tests for compareTo, equals, occursOn in all subclasses. | Kanan Ibadzade | Completed | 2024-11-03 | 2024-11-04
Milestone 3 | Refactor subclasses to integrate updated compareTo and equals methods. | Efe Gur | Completed | 2024-11-02 | 2024-11-04
Milestone 3 | Update compareTo in Appointment for sorting by startDate, endDate, and description. | Efe Gur | Completed | 2024-11-03 | 2024-11-04 | We have a missing group member who has not been contributing for milestone 2 and milestone 3. Member name: Winston Kim